## Issues
Project name | Project Type | Facility Type | Category | ITBC | Issues
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | Limited road access to project site for large and heavy equipment.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | Damage of public facilities (jalan kampung) due to heavy vehicle and frequent traffic flow.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | High volume of traffic causing congestion around project site vicinity.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | Complaints from nearby local residents due to increase in traffic during project execution.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | High volume of traffic especially during SAMUR shutdown and coincide with peak construction activities.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | Delay in construction activities resulted in insufficient fabrication laydown area during project execution.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | Late approval from SOGIP for additional fabrication laydown area, if required and subsequently results in additional time required for preparing the additional requested area.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | Availability of existing accommodation around project site for construction camp/workers accommodation (to include owner's personnel allocation).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Vehicle Refuelling for Industrial Usage | Unavailability of refuelling station for industrial usage.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | Unavailability of required heavy lift equipment during project execution due to other concurrent projects in the vicinity of project site.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Local Skilled Manpower (including vendor) | Insufficient local skilled manpower due to other concurrent projects around project site area (e.g. welders, fitters).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Project activities (e.g. driven-piling) causing interruption to PCFSSB plant operation (vibration).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Congestion of marine traffic may afect loading of PCFSSB or offloading Project Z materials and equipment.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Riot, worker differences, different culture, not harmonize
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Lost of materials at site
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Substance misused (alcohol and drugs)
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | Local Sabah contractor not familiar with PETRONAS HSE requirement
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | Restriction on non-Sabahan workers to work in Sabah.
PROJECT Z | Brownfield | Onshore - Production | Others | Weather and Sea Condition with respect to Construction and Transportation | Contractor not aware on the local weather and sea condition that affect construction activities and transportation.
PROJECT Z | Brownfield | Onshore - Production | Others | Weather and Sea Condition with respect to Construction and Transportation | High water table
PROJECT Z | Brownfield | Onshore - Production | Others | Nearby Local Resident Disturbance | Shortage of water, noise & dust pollution and heavy traffic affecting nearby residential area.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | Disturbance to marine life and PCFSSB jetty due to dredging activities.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | Lack of cost competitiveness with only one (1) dredging Contractor can perform dredging activities.
PROJECT Z | Brownfield | Onshore - Production | Others | Local Authorities Requirement on Marine Transportation and MOLF | Lack of information on the local authority requirement on marine transportation and MOLF in Sabah marine area.
PROJECT Z | Brownfield | Onshore - Production | Others | Interfacing with Concurrent Construction Activities (pipeline, jetty) | Potential delay due to simultaneous activities by different subcontractors due to lack of integration and coordination.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Clash of work priority towards the end of construction activities prior to handover to commissioning which can potentially leads to HSSE incidents.
PROJECT Z | Brownfield | Onshore - Production | Others | Pinching and Lost of Manpower due to Nearby Major Projects | Insufficient manpower during construction phase (skilled workers).
PROJECT Z | Brownfield | Onshore - Production | Others | Congestion during Peak Construction Activities | Potential HSE incident during peak construction work
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Bulk Construction Materials (sand, cement) | Insufficient of bulk construction materials (e.g. sand, cement)
PROJECT Z | Brownfield | Onshore - Production | Others | Subcontractor Selection | Incapability of subcontractor selection during EPCC stage
PROJECT Z | Brownfield | Onshore - Production | Others | Contractor and Subcontractor Productivity | Low productivity of local Sabah Contractors.
PROJECT Z | Brownfield | Onshore - Production | Others | Utilization of Gas Turbine from MLNG to Project Site | Impact to project schedule due to uncertain project sanction and late release of equipment towards end of construction.
PROJECT Z | Brownfield | Onshore - Production | Others | Utilization of Gas Turbine from MLNG to Project Site | Risk to plant performance due to not part of EPCC warranty.
PROJECT Z | Brownfield | Onshore - Production | Others | Early Site Posession | Late approval by SOGDC for site possession.
PROJECT Z | Brownfield | Onshore - Production | Others | Plot Plan Optimization | Processing plant for Project Z is next to non-manufacturing area of PCFSSB resulting in exposure to hazard.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Obstruction due to 2 nos. of new filter vessels | Lifting of existing vessels over the newly installed ones
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Obstruction due to 2 nos. of new filter vessels | Limited crane access to existing vessels.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Obstruction due to 2 nos. of new filter vessels | Existing ground surface is gravel paving.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Power cables hanging across main access into MS. | Overhead cables will obstruct during equipment and construction machineris access, e.g. cranes, filter vessels etc.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Existing earthing copper strip | The copper strips may be damaged by excavation work for both filter vessels foundations and cable tranches.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Underground cables | Live power cables shall be protected or relocated.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Underground cables | There is no indication at site where these suspected cables from from.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Traffic movement at junction of Road TP5 | There will be heavy vehicles going in or coming out from this junction. Also, possibly vehicle parking beside Road TP5. Construction cabins may also be place near the junction.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Traffic movement at junction of Road TP5 | Adjacent villegers will use this junction for access.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Access road | Create awareness to the villagers
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Access road | Meet with JKK before the construction starts place
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Access road | If there is any damages during construction, the contractors will make new surfacing for the existing accessing roads
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Access road | Propose csr activities to resurface the road from the main road junction to the main gate in according to existing size upon completion of project.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Equipment laydown | There is limited space for equipment laydown within MS (which include construction tools).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Emergency assembly point | Maintain the same assembly point as existing assembly point (in MRCSB), as there is no other possible area.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Tools and equipments | Security of tools and equipments, as the surrounding area is prone to theft (based on past experience).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Construction wastes | Rubbish and construction waste may be dispose at unauthorised/ approve dumpsite.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Emergency access route and access panic door | There is only one main entrance for access into/ out the MS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Support for raised floor | Noticed the Raised Floors in the instrument room of Control Building are just supported by planks (near cable entry area). This is not accetable and it's a HSE concern.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Foundations for new equipment | There will be 2 new filter vessels of larger capacity and size than existing ones. Due to the MS is situated at "cut ground" area, there may not be any piling but just large pad footings.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Existing underground facilities | There are existing underground facilities, i.e. cables, pipes etc. as indicated in As-Built drawings. Some may be identified and some are not. These facilities may be damaged due to excavation or heavy vehicles running over.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Access road to MS | Due to current "narrow" road to MS, there is a concern of heavy vehicle access, i.e. crane.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Existing valves | For replacing of meters and regulators, there may be high possiblity of block valves passing. These valves have been used without shutdown for the last 20 years. These valves passing will only be known after removing replacement spools.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Metering shelter | It is found that the MS is in a lightning prone area. Although the surrounding of the MS is higher, lightning risk is consider high.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | PMT registration | There are 2 new filter vessels (pressure vessels) to be installed and these require DOSH approval for design and installation.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | Scaffolding | Hold meetings/ discussions between PMT and Operations on PTW implementations within the metering station.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | CIDB approval (COA) | CIDB has imposed all imported material to be verify and certify before bring into Malaysia. This has caused much difficulty for both PMT and contractor to comply due to the elaborate processes and testings.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping route | Inlet piping to new filters is yet to be confirmed
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Access of fabricated pipe into MS | Pre-fabricated pipe spools may be too large for the existing gate access. Need to look into temporary dismentle existing access gates to make way for the large pipe spools.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Sequence of construction | The MS is under operation & running, and there is no shutdown since it started operation. Part of some of it piping are experiencing continous condensation, and need to carry out welding work.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Pressure vessel | Lifting of filter pressure vessels and its complications.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | WPS for pipeline | There is a need to produce new WPS for all new projects, as per the relevent PTS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Hot tapping | General area of hot tapping has been identify but not the exact location. This very much dependent on the existing pipe condition and wall thickness
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Painting maintenance | Some pipe supports need to be changed and depending on result of pipe stress analysis during Detailed Design.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | All tie-ins between existing and new flanges, and the existing flanges are old, thus there is possibility of flange surface damages (e.g. scrathes or cracks) upon removal of pipe spools.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | There is also possibility of block valve passing due to aged facility (20 years)
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | The above will lead to delays in completing the tie-ins.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | Generator set for power supply | On many occassions, contractor did not get the relevent approval from authorities and has resulted to delay and cost overrun.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | UPS | There is a need to have a backup UPS while charging the newly installed ones. This backup will be from the existing UPS where the electrical power strored may be lesser due to "old" unit.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | RGT2 Server inside Control Building | TNB intends to relocate the main supply meter from within MS to outside MS fencing. It requires a temporary power shutdown of MS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | RGT2 Server inside Control Building | It is not known whether RGTSU server inside the control building has temporary backup power to cater for temporary power blackout due to the relocation works.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Power and Instrument Cables | There are both E&I cables to be replaced and these existing ones may run differently from As-built drawings. Wrong cables may be terminated or cut, which may resulted to accident.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Multi Cable Transit (MCT) | Existing MCT may not be enough for the additional new cables.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Lightning pole | Lightning poles need to be removed when laying the new replacement cables, and will expose worker to potential lightning strike during construction.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Others | SOCSO requirements | DERMAGA is required to provide the list of names who will be working in MS and these people shall be registered and contribute to SOCSO
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Access to Elevated Cable Trays | Limited access to work area prior to shutdown
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Replacement of Brackets and Supports for Junction Box and Field Instruments | Physical verification of junction box and field instrument supports and brackets have not been conducted. Only visual verification is made.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Corrosion of Cable Trays | Galvanic corrosion may occur between dissimilar cable tray materials i.g. stainless steel vs. gulvanized
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Dismantling and Installing of Existing and New System Cabinets | There is an existing platform on top of the system cabinets that will obstruct the lifting process for replacing the existing system cabinets
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Working Space Constraints inside SCR 1, 3, 4 & 5 | Gas detector system panels replacement for SCR 1,3,4 & 5 may have working space constraints due to PCDM works inside these SCRs.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Disposal of Dismantled System Panels | Dismantled system panels need to be placed temporary while awaits approval from Asset Disposal Committee (ADC).
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | Installation of UPS | Need to know where to put the battery and UPS panels within SCRs
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Aditional Scope of Work for Sedia Teguh | MRCSB have not finalized the additional scope of work for Sedia Teguh for this package.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Loop Test Inspection and Verification | Not enough manpower from MRCSB to verify loop tests.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Logistics Plan | Contractor's logistic plan is yet to be confirmed and approved by MRCSB.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | Power Supply for New Controllers | Power supply for the new controller is a bit far for the new controllers based on site survey
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Limited working area in SCRs
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | Limited temporary storage area for panels.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Manpower Access | There are approximately 9000 workers during TA and it is expected that congestion will happen at all manpower entrances.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Working until Extended Hours | Possibility of working until extended hours and it requires the renewal of all issued PTWs on that day which will shorten the working period for extended hours.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Existing Raised Floor Panels | Improper existing raised floor panels reinstatement
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Existing Raised Floor Panels | Inadequate existing raised floor panels strength to support new panels and furnitures.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Asset Disposal | To identify temporary disposal area during TA
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Work Pack 22 (replacement of transmitters) | Work Constraints.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | WP 30 (lightning arrestor) | Several working at height method to be considered and to be assessed
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | WP 21A (Shutdown valve) | Interfacing of work sequence & scoping between Hyperwave & Dominant
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Equipment Lifting and Preparation | Congestion in the plant during TA and limited working space.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Equipment Lifting and Preparation | The existing vessels may not have any lifting lugs/trunnions.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Static Equipment | Condition of Existing Equipment Holding Down Bolts and Nuts | Bolts and nuts for existing vessels may be not in good condition.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Work Sequence during TA | Multiple contractors working in the same area during TA.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Contractor's Project Team members may not be on site/part time.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Some of the team members may not have enough experience due to market demand for skilled workers (This TA requires approximately 9000 workers)
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | There is no Engineering Representative of Contractor at site during Construction Phase.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Some workers may not be familiar with MRCSB HSE Requirements.
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | WHP and CPP fabrication area | Potential congested area and limited crane access at laydown/ fabrication area
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Delay of BOKOR CPP loadout affects WHP jacket construction | Limited crane access at the fabrication area
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Flooding at fabrication no4 and no5 | Water flooding at Fab no4 and no5
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Flooding at fabrication no4 and no5 | Safety hazard due to flooding of electrical and Instrument cable
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Flooding at fabrication no4 and no5 | Potential construction equipment damage (i.e. genset, blower)
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Skidded equipment | Obstruction during skidding of equipment (i.e. structural bracing)
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Dimensional Control for critical points between topside and jacket | Concern on the alignment of jacket and topside
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Gap during inspection | Insufficient gap during welding inspection at bracing area
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Availability of Vendor data for Instrument panel | Vendor data for equipment not yet available for E&I room and LER
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Fixture quantities differ between architectual and electrical engineering drawings | Potential discrepancy between architectual and electrical engineering drawings
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Strength jack support beam | Location of strength jack support beam yet to be identified
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Transportation plan availability | Transportation from Installation Contractor not available due to pending award
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Soil Investigation for WHP topside | Pending Plate Bearing Test (PBT) at one location WHP Topside fabrication area
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Interface between Contractor and Vendor | Interface issue between Contractor and Vendor that lead to lack of information for Vendor design
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Contigency for material | Potential insufficient of structural material due to fabrication error.
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Stiffner in Launch Craddle | Space constraint for welding of stiffner in Launch Craddle
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Stiffner in Launch Craddle | Welding configuration yet to be finalized (full penetration vs fillet)
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Alignment of skid beam | Alignment and straightness of skid beam for drilling rig entry after removal of padeye
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Construction sequence | Potential optimization under current proposed construction sequence
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Interface with OIC | Pending interfacing plan with OIC (bumper guide installation etc.)
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Fabrication Engineering requirement | Potential weld on weld, seam orientation not meeting requirement as per PTS
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Contractors | Access route has not been confirmed in detail for Equipment and Manpower
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Common Facilities Management | 80x90 plot is available for AGO Project. However, the detail of the plot usage has not been discussed.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Others | Permit To Work (PTW) Issuance | Permit To Work (PTW) to adopt existing Plant PTW System
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Critical Equipment | The accessibility and all turning radius along the access route for the critical equipment (possible 60m length of the exhaust stack) are yet to be explored
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Existing underground facilities | As built drawings for underground utility available but not updated since 1998
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Soil bearing capacity & ground level contour | No as built document for soil investigation & topography on the proposed sites
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Underground Scanning at Existing Plant Area | The underground scanning conducted might not be accurate specifically at the existing area (yet to be done)
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Additional Weight on Existing Raised Floor | New DB installation located on existing raised floor at FAR Building GPP6 2312 will provide additional weight to the raised floor
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Space Constraint for New Pipe Support | There is a possibility of space constraint for the new pipe support foundation (42" tie-in). This will lead to difficulties in constructing the foundation
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Fire Proofing | The new steel structure facilities may need fire proofing, considering the existing surrounding equipments are fire proofed.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Static Equipment | Supporting Facilities for Equipment Delivery | There is no study or more information on supporting facilities surrounding the project site for delivery of materials and equipment.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Static Equipment | Lifting Plan | There's a need for a Lifting Plan for the installation of the AGOs (considering horizontal or vertical AGO configuration).
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | New Fire Monitor & Hydrant | Possibility to install two fire water hydrant & monitor at the new AGO location and this is applicable for both GPP5 & 6 AGOs.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | Pipe Pressure Drop at New 42" Piping | It is proposed to install a 90m 42" dia acid gas piping. This will lead to a possible high pressure drop. Pipe length - To ensure Pressure at inlet of AGO
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | Verification of Existing Cable Trench | Existing cable trench condition has not been checked and verify.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Instrument | Instrument Cable Route | The instrument cable route to be confirmed
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Source of Temporary Water Supply | Temporary Water Supply source for the project use need to be identified
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Source of Temporary Power Supply | Temporary Power Supply source for project use need to be identified
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Crossing/Transporting of Equipment below Pipe Rack Structure | Space/Height limitation - Existing pipe rack towards site location maximum height is ?m and width of ?m (to be determined by PMT)
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Limited Access and Working Area for HRSG | Limited access and working area for the replacement of pressure parts of 2 units of HRSG.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Facilities | Inadequate space area for all temporary facilities (site office, equipment/material laydown area, car park, warehouse, etc..)
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Demolition Work | Demolition work may affect surrounding structures and facilities (such as cracks and vibrations).
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | AGB Boilers Access | Difficulty to bring out existing AGB boilers and bring in new AGB boilers in to the main building due to limited door size.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Relocation of Existing Facilities | Relocation of exisiting facilities may be required during construction.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Modification of Existing Pipe Racks and Pipe Support Foundation (new foundation / modification of existing foundation) | Existing pipe racks/supports may need modification to cater for new equipments (upon site survey)
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Others | Permit to Work (PTW) | Untimely issuance of PTW.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Temporary Facilities | Requirement of utilities utilization (e.g electricity, water, instrument) during Construction and Commisioning | GDC KLIA plant is unable to supply required utilities for construction activities during production peak time.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Height Restriction for Outdoor Lifting | Crane lifting activities is being restricted by the flight path limit.
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | Congested access from TIGA Main Gate during TA
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | The access to project site will go through pipe bridges
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | Multiple PTW applications for multiple asset owners
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Project Site Platform Elevation | The difference of height between those two platform levels is too large
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heat Radiation from Nearby Slug Catcher Flare (A6331AB) | Heat radiation contour of slug catcher flare may encroach project site
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Construction Near to the Trunk Line including LNG Rundown Line | The trunk lines are very near to the proposed project site
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Lift and Soil Condition | Soil condition may not be able to cater for large load during lifting
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Shallow Ground Water Level | High ground water level will make deep excavation difficult (for aeration basin)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Seawater Discharge Pipe from Aeration Basin | The seawater discharge pipe will be obstructed by the existing trunk lines, 3 feed gas lines. spill over line, shore protection, fencing, cables
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Seawater Discharge Pipe from Aeration Basin | Elevation from the aeration basin until the seaside liquid head
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Seawater Discharge Pipe from Aeration Basin | Possible underwater trenching
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Seawater Discharge Pipe from Aeration Basin | Possible pipe clogging
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Verification of Existing Firewater Ring | Inadequate existing firewater lines at the fire training ground
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Pipe Routing for New Acid Gas Line for MLNG DUA and MLNG TIGA including BF Water, HP Steam and Utilities | This pipe routing is yet to be confirmed and agreed by plant owner
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Non-Metallic Pipe for Sour Gas Line | Metallic pipes proposed may be too heavy for the existing foundation and structure to carry
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Electrical | Existing Underground Cables at Project Site (including instrument cables) | Difficulty in relocating all existing underground cables at the proposed project site
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Instrument | Instrument Tie In to Main Field Station (MFS) / MPCC | Congestion and space limitations in MFS basement (if this option is adopted)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Laydown and Temporary Rest Area Location | Difficulty in getting approval to use SKG area
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Laydown and Temporary Rest Area Location | Pipeline ROW within the SKG area
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Manpower Transportation from TIGA Main Gate to Project Site | PMT is yet to apply for shuttle services from plant owner
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Equipment Transportation | PMT has not consider equipment transportation using barge to project site
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Utilities Supply for Construction | Temporary utilities supply for construction are yet to be confirmed
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Waste Disposal Plan (i.e. Construction Waste, Scheduled Waste, Domestic Waste) | PMT has yet to address waste disposal during construction
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Preservation of Equipment upon Arrival on Site | Lesson learnt from Train 9 project (i.e dessicants were not replaced after exceeding their lifespan)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Availability of Skilled Manpower Nearby | PMT has yet to explore the availability of local skilled manpower
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Interface with MLNG Electrification Project | Locations of new substations for MLNG Electrification Project are yet to be determined
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Monsoon and Haze Season (High Tide) | Work productivity is lower during monsoon/haze season
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Tie-Ins (BF Water, HP Steam, Utilities) | Tie-ins for BF Water, HP Steam and Utilities have not been identified
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Integration between Main Contractor and Licensors | Lack of coordination between main contractor and licensors, leading to incomplete work scope of vendor supplied packages / equipments
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Custom Clearance | Late custom clearance due to late application of tax exemption from MITI
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Authority Approval to Start Work (e.g. DOSH) | Late approval given by DOSH to start work due to last minute application by Contractor / Project Owner
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Delivery Schedule for Equipment | PMT has yet to finalize equipment delivery schedule to support Required On Site (ROS) dates
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | eMOC Management | Compliance to MLNG specific requirements (Operation, Maintenance and HSE)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Packaged Equipment Transportation Warranty | Possible damage on the packaged equipment during transportation
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Demolition / Isolation of Existing Equipment | The schedule for demolition is not yet determined
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Demolition / Isolation of Existing Equipment | Interdependency on MLNG Electrification Project on the area required (demolition area of AGTO MLNG DUA)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Special Tools Requirements | Delay in construction activities due to unavailability / late delivery of special tools
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Valid Sarawak Work Permit (EPCC, PMT and FEL 3 Team) | No valid and prolong approval of Sarawak work permit
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | River and Railway Crossing for Pipelines | Kertih River and railway crossing for utilities and feedstock.
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | River and Railway Crossing for Pipelines | Unclear requirements and yet to engaged with relevent authorities
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | Existing auxilary boiler foundation is not removed which will obstruct the construction of new proposed boiler
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | Inadequate space to locate new boiler footprint
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | Limited access to the Option B boiler location
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Height and Width Clearance within UK for Logistic Purpose | Maximum height and width clearance for equipment delivery and crane access are not confirmed yet
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Land Acquisition for External Pipeline Area including Access | The Operator of new ROW is not finalized
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Brownfield and Greenfield Demarcation | 4 different brownfield areas (GPK, PGU, UK and KTSB) with 4 different permit systems and 2 different greenfield areas (new pipe racks and DMC)
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Brownfield and Greenfield Demarcation | Interface issues with different owners
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Civil, Structure & Building | Existing Pipe Racks and sleepers | Inadequate space for new pipings on existing pipe racks and sleepers
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Civil, Structure & Building | Existing Pipe Racks and sleepers | Existing pipe racks and sleepers are owned by multiple owners
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Obstruction at new AFC Area | There is an existing valve at the AFC future area which is not indicated in the latest P&ID and Plot Plan
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Valves Passing | Possibility of valve passing at existing block valve (e.g. HP steam, Condensate, CO2, Utilities) for tie-in works
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Code Demarcation for External Pipings (Pipeline) | Code reference used for existing ROW (KTSB) is unknown
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing Electrical and Instrument Cables in UK | Inadequate space for new cables from Substation 01 to outside fencing in existing direct buried cable trench
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing 33kV GIS Switch Gear | Servicing of existing circuit breaker is in PGB DMC SOW or not
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Instrument | Modification of Instrument Facility at UK Control Room | Congested cables under the raised floor and limited space within UK Control Room
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Temporary Facilities | Laydown Area | Limited laydown area within Utility Kertih facilities.
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Project Execution during Operation (SIMOP) | Working in live plant
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Tie-In Points at DMC Plant | DMC plant configuration and plot are unknown
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Tie-In Points at DMC Plant | Requires TNB approval if encrouch transmission line ROW
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | EIA Requirements | Long approval process
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Overall Project Schedule | Open-ended execution schedule make it difficult to align with UK/PGU (A2 station) TA windows for tie-ins
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | Limited road access to project site for large and heavy equipment.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | Damage of public facilities (jalan kampung) due to heavy vehicle and frequent traffic flow.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | High volume of traffic causing congestion around project site vicinity.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | Complaints from nearby local residents due to increase in traffic during project execution.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | High volume of traffic especially during SAMUR shutdown and coincide with peak construction activities.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | The integrity of existing facilities that is foreseen to be used during project execution.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | Delay in construction activities resulted in insufficient fabrication laydown area during project execution.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | Late approval from SOGIP for additional fabrication laydown area, if required and subsequently results in additional time required for preparing the additional requested area.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | Availability of existing accommodation around project site for construction camp/workers accommodation (to include owner's personnel allocation).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Vehicle Refuelling for Industrial Usage | Unavailability of refuelling station for industrial usage
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | Unavailability of required heavy lift equipment during project execution due to other concurrent projects in the vicinity of project site.
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | Insufficient local skilled manpower due to other concurrent projects around project site area (e.g. welders, fitters).
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Project activities (e.g. driven-piling) causing interruption to PCFSSB plant operation (vibration)
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Congestion of marine traffic may afect loading of PCFSSB or offloading Project Z materials and equipment.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Riot, worker differences, different culture, not harmonize
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Lost of materials at site
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | Substance misused (alcohol and drugs)
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | Local Sabah contractor not familiar with PETRONAS HSE requirement
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | Restriction on non-Sabahan workers to work in Sabah.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | Contractor not aware on the local weather and sea condition that affect construction activities and transportation.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | High water table
PROJECT Z | Brownfield | Onshore - Production | Others | Nearby Local Resident Disturbance | Shortage of water, noise & dust pollution and heavy traffic affecting nearby residential area.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | Disturbance to marine life and PCFSSB jetty due to dredging activities.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | Lack of cost competitiveness with only one (1) dredging Contractor can perform dredging activities.
PROJECT Z | Brownfield | Onshore - Production | Others | Local Authorities Requirement on Marine Transportation and MOLF | Lack of information on the local authority requirement on marine transportation and MOLF in Sabah marine area.
PROJECT Z | Brownfield | Onshore - Production | Others | Interfacing with Concurrent Construction Activities (pipeline, jetty) | Potential delay due to simultaneous activities by different subcontractors due to lack of integration and coordination.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Clash of work priority towards the end of construction activities prior to handover to commissioning which can potentially leads to HSSE incidents.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Insufficient manpower during construction phase (skilled workers).
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Potential HSE incident during peak construction work
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Insufficient of bulk construction materials (e.g. sand, cement)
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Incapability of subcontractor selection during EPCC stage
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Low productivity of local Sabah Contractors.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Impact to project schedule due to uncertain project sanction and late release of equipment towards end of construction.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Risk to plant performance due to not part of EPCC warranty.
PROJECT Z | Brownfield | Onshore - Production | Others | Early Site Posession | Late approval by SOGDC for site possession.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Plot Plan Optimization | Processing plant for Project Z is next to non-manufacturing area of PCFSSB resulting in exposure to hazard.
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Single Lift vs Multiple Lifts | Constraints on multiple lifts since we need to do piece by piece
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Single Lift vs Multiple Lifts | Longer duration for multiple lifts
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Single Lift vs Multiple Lifts | On both lifts, need to identify clearance to the existing facilities (i.e. cooler, bridge, etc)
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Vessel Crane Availability | The required vessel crane may not be available for the lifting activities
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Mooring Line of Vessel | Soft mooring is subject to Operation approval
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Mooring Line of Vessel | If soft mooring is not allowed, Dynamic Positioning (DP) vessel may be required
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Anchor Pattern of Vessel | Anchor pattern is yet to be developed accordingly
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Anchor Pattern of Vessel | Anchor pattern is subject to Marine Captain approval
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Heavy Lifting Sequence | The heavy lifting plan for single lift/multiple lifts has yet to be developed
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Additional Load on Existing Structure | Acceptable additonal load
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Offshore Structure Welding Activities | The nos of offshore structure welding activities have not yet determined
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Support and Bracing Requirements | The support requirements for installation is yet to be studied and finalized (i.e bracing requirements, etc)
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Static Equipment | Installation of Static Equipments | Static equipments to be installed in one skid or installed individually
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Pipe Routing | Pipe routing is quite congested and complicated
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Tie-In Points | The nos of tie-in points and methodology for tie-in activities have not been finalized
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Turn-Around | Short TA period
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Overall Contracting Strategy (OCS) | OCS has not been finalized yet
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Overall Project Schedule | Overall project schedule has not been developed
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | PMT Org Chart | PMT Org Chart for various project phases has not been identified
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Offshroe Installation of Deck Extension | The offshore installation methodology including transportation concept is yet to be determined
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Congested work during TA | There will be concurrent activities either with Operation or Maintenance teams during TA
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | Route clearance constraints within PCML 2 (4m-6m height constraints)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | Unknown soil condition at proposed crane location
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | Damages to existing facilities during crane installation
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Heavy Lift' Crane Availability | Heavy lift' crane is not readily available during project execution
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Unknown Soil Condition to support Heavy Lift Activities and MOLF | Possible ground settlement and soil failure
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Construction of Material Off Loading Facilities (MOLF) | Undecided suitable location of MOLF
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Construction of Material Off Loading Facilities (MOLF) | Stringent local authorities and regulatory approval
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Construction of Material Off Loading Facilities (MOLF) | Schedule and cost impact due to construction of MOLF
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Civil, Structure & Building | Underground Facilities | Excavation activities will damage existing cables and pipes
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Piping | Tie-In Points and Routing | Insufficient capacity of existing pipe rack structures to carry additional new pipings
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Piping | Tie-In Points and Routing | Space availability for new pipe structures
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Inadequate temporary facilities area for PMT and Contractors within PCML Plant 2
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Limited Laydown Area during TA | Limited laydown area of bulk materials for SUMILAU project due to concurrent TA activities
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Schedule Impact due to TA Date Change | Others | TA date may be earlier or later than planned date which will impact on project schedule planning
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Adverse Weather | Others | Adverse weather will affect work progress and interrupt construction work sequence
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Emergency Readiness Supporting Plant | Others | Existing emergency readiness system may not function at project site
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Theft in Plant during TA | Others | Loss of material / equipment during TA
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Long Holiday Season | Others | Loss of productivity and leads to schedule impact
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Low Performing Contractor/Vendor | Others | Low productivity, low quality performance and unacceptable HSE performance which may lead to possible work delay
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Local Grievences | Others | Sosio-economy complaints
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | Late issuance of PTW
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | Changing shift of JHA reviewer and approval of plant owner which lead to late PTW approval
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | Plant trip due to hot work activities in live plant
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | Latest update of supporting documents for PTW are not available
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Concurrent Construction Activities by Different Contractors | Others | Interruption of construction activities due to other nearby contractors (e.g. road closure due to heavy lifts)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Lack of Resources during TA | Others | Pinching of manpower / equipment
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Lack of Resources during TA | Others | Job hopping by workers
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Competency of Workers | Others | Lack of competence workers
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Competency of Workers | Others | High attrition rate among contractors and subcontractors
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Competency of Workers | Others | Fake certification of workers
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Special Material WPS | Others | Lack of qualified welders for specialized material
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Insufficient FEED Information | Others | FEED information is found to be inadequate based on Detailed Engineering Management Manual (DEMM) (e.g. hydraulic study, electrical load study, etc.)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Boiler Vendor and EPCC Contractor SOW Dispute | Others | Unclear scope demarcation between boiler vendor and EPCC contractor
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Interface between PMT and Owner | Others | Miscommunication between PMT and Owner
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | SOCSO requirements | Others | However, DERMAGA claimed that they will have short-term workers (< 1 month period) and proposed to provide workmen compensation insurance instead of SOCSO, in which will provide the same insurance coverage during work.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Requirements, Drawings, and Procedure | Concern on sequence of heavy equipment throughout existing piperack/ pipebride within RAPID.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Requirements, Drawings, and Procedure | Yet to identify e.g route, dimension, method of excavation. Plot plan cannot be determined with limited info from vendor packages for ETP section
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Underground Detection | UG detenction yet to be done and reference only based on previous RAPID I&O drawings.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Poor/no coordination between vendor scope and engineering consultant scope may affect execution timeline
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Cost for excavation varies depending on brownfield/greenfield identification. Shoring requirement to be identified
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | ETP pit excavation depth yet to be identified. Current pit design stands at 3-4 meters
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Fire zoning study yet to be done.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Cost for piling varies depends on brownfield/greenfield identification.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | No issue based on latest information given by RAPID management
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | May affect ISBL water run-off
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Existing benchmark may not maintained aftre RAPID execution phase completed hence accuracy issues if blindly utilized. May affect tie-in issue.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Interface study yet to be done
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Lighting requirement is not yet considered especially for skid-related lighting as vendor is yet to be appointed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Full estimation of power usage and output pending confirmation from other Engineering discipline team hence affecting overall MTO for project.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | MTO in draft mode, only for Nutmeg (feeder). MTo for ETP still not available However, preliminary input from FEED studies has been received
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Information on power input from other discipline yet to be identified
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Lesson learnt from PMT: EX requirement for electrical equipment was not spelled out comprehensively inside SOW and ITB hence resulted to CO.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Cable | Possibility of underground cable routing once IDC done might interfere with other disciplines' work. All cable routing is planned for above ground at this stage.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Cable | Possibility of no/ limited underground cable entry from existing cable duct/ cable trunk as well as substation cable cellar entry.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | CP for the entire Titanium OSBL project is yet to be considered.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | Yet to be developed. Probable commercial issue with PRPC UF if using permanent power during project execution (commissioning phase)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | Yes, special requirement needed. Requirement study has been done by EPCM Contractor PMT
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Ergonomics aspect for instrument field devices' location yet to be considered. Operation yet to be engaged at this stage
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Probable conflict on shutdown requirement from Owner (PRPC UF) e.g. treated water
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Probable damage to existing RAPID FOC backbone during OSBL execution Requirement to work inside FAR 475
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Possibility of no/ limited underground cable entry from existing cable duct/ cable trunk as well as MCB cable entry
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Lesson Learnt from P14: Inconsistent interface information resulted to inconsistency between engineering and construction that lead to delay.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Cable laying routing depends on other disciplines' readiness to finalise
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Material Management | Poor storage for sensitive instrument item leads to damaged item prior field installation
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | Yet to identify the PTW system to be used
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | Yet to receive information
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | RCP guideline may differ since RAPID execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | Unavailability of Project Communication Procedure
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | Yet to develop.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | Yet to be developed
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | CIDB approved training for competent traits/crafts to be made available. Does the central permitting team still available to assist?
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | Systemization yet to be developed for priority system
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | Waste management contractor given PALON contract during RAPID might not be available post RAPID project execution.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | Piping: Scope available to do tie-in to existing facilities. Condition of the tie-in is yet to be verified.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Systemization | Late/ no prioritization may leads to resource redundancy during execution phase
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | Partial shutdown needed for electrical & instrument tie-in (ELE) Potential hot-tapping for ETP piping tie-ins and 3 mentioned services for interconnecting tie-ins
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | Fire Safety Design Philosophy yet to be developed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | PMT have develop the tie-in list. However isolation list is yet to be develop. Roles and responsibilities between stakeholder yet to discussed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Training | Yet to develop
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | EMP yet to be developed
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Training | Yet to develop
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Probable shutdown for certain lines during tie in works for existing lines due to drop valve requirement to existing butterfly valve.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Butterfly valves lug type with no spool after valves. To remove blind, need to drop valve for WP, IA & SW
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Hydrotest and Non-destructive testing (NDE) work during execution may encroach Nutmeg ISBL and neighboring Prefchem plants
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Shutdown to existing facilities may required/ hot tapping due to cut/weld execution method
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | No issue. Acoustic insulation has been considered at this stage.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Execution timeline for each piping material type differs in term of fabrication and erection due to different requirement and technicality needed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Lesson learnt: Underground GRE used for RAPID FW resulted to underground leakage which leads to low pressure/ non-functional fire fighting equipment for many RAPID packages including P14.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Water removal location/ route post hydrotest and flushing activities yet to be identified
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Weight limitation to be checked considering partial usage of existing piperack
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Yet to be developed
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Testing requirement yet to be elaborated
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Execution timeline for each piping material type differs in term of fabrication and erection due to different requirement and technicality needed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Piping Pre-qualification | 10 production joints requirement increases cost for EPCM Contractor and Package Contractor. Lesson learnt: Ever-changing welder personnel leads to delay in getting enough personnel to be qualified for field welding works.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Unclear scope demarcation between vendor and EPCM contractor may lead to delay during detail engineering
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Lesson learnt - Support team availability issue from vendor during mechanical equipment cold run
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Engineering Interface | Potential engineering mismatch between Engineering and vendor package. This may lead uncertain interfacing engineering to PC contractor during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Tank | Vendor yet to be proposed for detail design (Package Contractor). Tank hydrotest procedure cannot be established due to no detail design yet. Water disposal post-hydrotest yet to be discussed.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Static Unfired Item/ Vendor Package | No issue. Space available during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Static Unfired Item/ Vendor Package | Foundation study was not done with vessel hydrotest (CVS).
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Discipline Related Material | Lesson learnt from RAPID: Pressure gauges procured and installed by vendor were not as per DOSH requirement resulting to double work in procurement, field installation and testing
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Provision for utilities tie-in for TCF Utilities (land rental, potable water, electricity, internet) charges
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Communication means (walkie talkie, TDRS) between PMT and Package Contractors during execution yet to be established
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Potential grow project within PIC are still unknown to PMT
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | SPC availability for rental, SPC catering yet to be known.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Site resting shelters provision/ availability yet to be determined for direct workers
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Incoming/ outgoing peripheral road from main road to proposed TCF location yet to be determined.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | JMP yet to be established
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | Not all the roads within PIC cater for heavy haulage (CVS). All roads inside PIC are already completed up to wearing coarse.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Material Receiving/ Outgoing Documentation | Potential poor material preservation without dedicated procedure and trained personnel resulted to execution delay.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Construction Execution | Transportation requirement and means for EPCM Contractor and Package Contractor yet to be established.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | No OOG equipment planned so far.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | Concrete batching plant not available

## Action Items
Project name | Project Type | Facility Type | Category | ITBC | Action Items
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To conduct further logistic study by FEED Contractors during FEED on land transportation access to the project site.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To identify bulk equipment or material for each mode of transportation land or sea frieght
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To include the reinstatement of damaged facilities to be borne by Contractor (EPCC scope).
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | To find out any future projects around project site vicinity and Sabah Oil and Gas Industrial Park (SOGIP) area and SAMUR turnaround activites
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | To include in ITB for potential Contractor to find out for best option for accommodation and access road to avoid traffic congestion during construction.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To verify the integrity of existing facilities by FEED Contractors and obtain permission from Facility Owner (to be included in FEED ITB) to cater for worst case scenario of 3.0 MTPA.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To explore options of constructing new MOLF to cater for the worst case scenario.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To provide temporary power supply during construction phase.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To explore and verify temporary power and water supply from adjacent SAMUR plant.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | Identify and verify adequate water supply for construction activity (for hydrotesting and flushing).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To consider access road during emergency response and to interface with SOGIP and SAMUR.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | To identify the dedicated stakeholder personnel for PMT and EPCC org chart to liaise with SOGIP on fabrication and laydown areas.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | PMT to initiate discussion with authorities and establishes project specific approval work process on fabrication laydown area to minimize schedule impact if indeed additional space is required
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | To identify additional area for shutdown (shutdown village) and to be included in site preparation work and to be included in FEED SOW.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | To include the construction camp requirements (including authorities, etc.) in the FEED ITB.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | PMT to survey accommodation availability around Sipitang.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | PMT to establish with HRM on reallocation package for the PMT personnel (to be finalised and approved before 1st site mobilization)
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Vehicle Refuelling for Industrial Usage | To put under EPCC scope to provide refuelling station for industrial use and dictate that only PETRONAS fuel and lubricant can be used. To be specified in Contruction Execution Plan (CEP) during FEED.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | To verify the availability of required heavy lift equipment in EPCC scope.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | PMT to provide Group Procurement (GP) crane suppliers in the project site area to EPCC Contractor. This information to be included in ITB EPCC
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | EPCC Contractors to engage with skilled workers from outside Sabah.
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | EPCC Contractor to identify SOW that can be undertaken by Sabahan workers and SOW cannot be undertaken by Sabahan workers (skilled and semi-skilled works).
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | PMT to liaise with Sabah State (Human Resource Ministry) and Immigration Office to understand Sabah requirements for employing non-Sabahan workers.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | FEED Contractor to carry out assessment on the best method for piling without affecting adjacent plant operation.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | EPCC Contractor to conduct survey prior to construction activities to establish baseline of existing facilities conditions.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Damages to the adjacent PCFSSB plant caused by Project Z activities need to be rectified by EPCC Contractor.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | To conduct marine traffic risk assessment (MTRA) to simulate nos of marine vessels during Project Z construction phase against current PCFSSB marine traffic (including local fishermen and SFI activities).
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To separate workers camp / accommodation to different ethnic and nationality.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To establish fence and security for materials and equipment storage laydown area. and warehouse.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | EPCC Contractor to liaise with PETRONAS Security and Sabah Police on support for surveillance of materials and equipment storage laydown area nad warehouse.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To establish security system for foreign workers
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | PMT to engage with State Police and PETRONAS Security Head on security matters of Project Z during project execution.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | To include in EPCC Scope of Work as part of EPCC Contractor responsibility to train local Sabah Contractor to familiar and comply with PETRONAS HSE requirement.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | To develop HSE procedure for Project Z based on either greenfield or brownfield project (Note: Considering SAMUR plant is nearby, not sure full greenfield project could be implemented,e.g Train 9 project declared as Greenfield)
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | To establish Project Regulatory Approval Matrix to cover for local law and regulations, government regulations and statutory approvals (by FEED Contractors).
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | PD&T HR to assist on planning for work permit application for PMT.
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | To identify the dedicated stakeholder personnel for PMT and EPCC org chart to cater for working permit application and management.
PROJECT Z | Brownfield | Onshore - Production | Others | Weather and Sea Condition with respect to Construction and Transportation | EPCC Contractor to study te local weather condition and take into consideration in their Construction Execution Plan (CEP) i.e. Monsoon Season Plan.
PROJECT Z | Brownfield | Onshore - Production | Others | Nearby Local Resident Disturbance | Engagement with local community to be conducted through SOGDC.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | To perform EIA study.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | PMT to check with Sabah Port and Jabatan Laut on the requirement of dredging contractor in Sabah marine area.
PROJECT Z | Brownfield | Onshore - Production | Others | Local Authorities Requirement on Marine Transportation and MOLF | To engage with Sabah Port and Jabatan Laut in order to understand Local Authority requirement on marine transportation and MOLF
PROJECT Z | Brownfield | Onshore - Production | Others | Interfacing with Concurrent Construction Activities (pipeline, jetty) | EPCC Contractor as a single party to coordinate and manage multiple subcontractors and clear demarcation of SOW between the subcontractors and to be included in CEP.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | To establish SIMOP Plan during detailed engineering.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Systemization Plan to be establish during early stage of detailed engineering.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | To specify the requirement of systemization execution during 60%-70% of construction progress in EPCC SOW.
PROJECT Z | Brownfield | Onshore - Production | Others | Pinching and Lost of Manpower due to Nearby Major Projects | To include the manpower control during construction in the CEP which include body pass system for head count and productivity tracking purposes.
PROJECT Z | Brownfield | Onshore - Production | Others | Congestion during Peak Construction Activities | FEED contractor to provide details of construction strategy in Construction Execution Plan (CEP) to ensure safe working environment during peak construction period
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Bulk Construction Materials (sand, cement) | EPCC Contractor to include the source of bulk construction materials in CEP
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Bulk Construction Materials (sand, cement) | To identify potential supplier for bulk construction materials during FEED.
PROJECT Z | Brownfield | Onshore - Production | Others | Subcontractor Selection | EPCC contractor to produce subcontractor selection process under Procurement Procedure for PMT approval.
PROJECT Z | Brownfield | Onshore - Production | Others | Subcontractor Selection | Subcontractor evaluation procedure to be established by EPCC Contractor to be reviewed and approved by owner.
PROJECT Z | Brownfield | Onshore - Production | Others | Contractor and Subcontractor Productivity | Extended working hours
PROJECT Z | Brownfield | Onshore - Production | Others | Contractor and Subcontractor Productivity | Similar to item CR01:TF06.
PROJECT Z | Brownfield | Onshore - Production | Others | Utilization of Gas Turbine from MLNG to Project Site | To present the case to Project Steering Committee for direction.
PROJECT Z | Brownfield | Onshore - Production | Others | Early Site Posession | PMT to formally secure the proposed plot for Project Z from SOGDC by November 2019.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Plot Plan Optimization | FEED QRA study to take into consideration PCFSSB and expansion phase. FEED Constractor to design the Project Z plot plan incompliance with QRA report.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Obstruction due to 2 nos. of new filter vessels | Lifting plan to be thoroughly reviewed due to lifting over existing facilities. Steel plates to be placed over gravel paving.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Power cables hanging across main access into MS. | Mark presence of power cables by installing warning sign posts nearby.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Existing earthing copper strip | Conduct scanning or underground utilities detection to identify all undergrtound facilities before any work start, and produce a report for reference.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Underground cables | Verify the suspected underground facilities with "As-Builts" drawings and confirm at site, before start work.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Underground cables | Provide protection upon confirmation.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Traffic movement at junction of Road TP5 | It was decided that vehicle traffic at junction of Road TP5 is not a main concern, due to all the construction works will take place about 500m away from the junction. Furthermore, a Traffic Management procedure will be part of contractor's deliverables (as per PTS 18.03.03, Contractor HSE Management) for traffic control of this project. For site office cabins, these cannot be placed in site (must be at 3KM - 5KM away) Project signboard are fixed before the entrance to the plant
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Equipment laydown | An area allocated just outside the MS area, i.e. on left side of access road.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Equipment laydown | Avoid any trucks or trailers to park just outside the MS area (along access road).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Equipment laydown | Allocate a specified area within MS for hand tools and construction machineries temporary storage, (without obstructing existing MS operation).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Tools and equipments | Remind potential contractors to be extra careful during site visits period.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Construction wastes | Identify areas to temporary gather construction wastes and large waste bins may be used to temporary store it.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Construction wastes | verify whether any approval require from local authorities(Majlis).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Construction wastes | verify whether there is any need for a new EIA or adopt an existing PGB's EIA.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Construction wastes | Contractor to establish construction wastes management.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Emergency access route and access panic door | An emergency access route has been identified and the route is behind the existing control building which can be only used to exit the MS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Plot Plan, Layout & Heavy Lift | Emergency access route and access panic door | There is an existing Panic door going into MRC area. Liase with MRC for emergency access during the working hours and also an area inside as an emergency assembly point. (the area should be barricaded to prevent any person to wonder into the plant. There may be security personnel stationed during working hours.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Support for raised floor | Need to find other permenant supporting arrangement.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Support for raised floor | To verify other areas of similar condition for both instrument and electrical rooms.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Foundations for new equipment | Conduct soil investigation (SI) at new foundations area and the SI report to be verfied/endorsed by geotechnical engineer.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Existing underground facilities | Establish methods of identifyng existing cables/ pipe (Underground Utility Detection device), and conduct verification survey. Verification report shall be approved before any underground work commence.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Access road to MS | The crane size is determined by the weight of equipment and crane turning radius.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Access road to MS | However, It was found accessible during the previous project, i.e. LEKAS, which used similar capacity crane for lifting.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Existing valves | Based on experience, such passing is manageable or minimal.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Existing valves | Request potential contractor to prepare and make available all the necessary resources in case of severe valve passing.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Metering shelter | Metering shelter need to have lightning arrestor while working in it.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Civil, Structure & Building | Metering shelter | It is already included in the project work scope
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | PMT registration | Reconfirmation on the need for DOSH registration and other compliance requirement from other authorities.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | CIDB approval (COA) | To engage with CIDB early and avoid unnecessary delay due to late submission and approval.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Static Equipment | CIDB approval (COA) | Follow the requirements set by CIDB.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping route | It is confirmed that these new piping will go over the existing gas pipes.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping route | All the necessity measures need to be taken during the installation especially lifting over existing facilities, e.g. lifting plan, crane inspection, skilled manpower etc.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Access of fabricated pipe into MS | There is no issue due to the small sizes of pipes are used. (8 and 12 inch)
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Access of fabricated pipe into MS | Experience from LEKAS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Sequence of construction | Impose contractor for a Construction Execution Plan (CEP), to identify how the construction work is done and its sequence (for a safe construction work).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Sequence of construction | Identify in the CEP all critical activities that requires special attention.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Pressure vessel | No special issues as the weight of one vessel is about 1.5 - 2.0 ton, and the location are an open area, hence enough working space.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | WPS for pipeline | Ensure this requirement is included in the ITB.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Hot tapping | The control of gas flow in the pipeline need to be discussed with MRC (in order to achieve optimum flow during hot tapping), and also the time/ day to conduct hot tapping.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Hot tapping | WPS to consider wet condition due to continous condensation on pipeline surface.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Painting maintenance | Requires painting maintenance at area adjacent to these pipe supports.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | To check and verify valve passing at each block valves.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | DERMAGA to physically investigate/check and ascertain the condition (as permitted) of the flanges at the tie-in points.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | DERMAGA propose to stroke the valve to ABT. Detailed inspection plan will be submitted for approval by April 2019.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | Affected block valves are TP13-19 (for metering runs), TP20-25 (for regulating runs) and TP1-2 and TP6-7 (for dry gas package).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | DERMAGA will prepare required resources during tie-in considering physical completion of the tie-in locations and lesson learnt from other projects.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Piping | Piping Tie-Ins | All tie-in works will be done within 24 hours or until completion for each run.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | Generator set for power supply | Obtain approval from ST and notify DOE on the usage of generator set of more than 5kVA capacity.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | UPS | To get a temporarily portable UPS for standby.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | UPS | Alternatively, install the new UPS first then change the DBs later.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | UPS | To get a temporary power supply from TNB while charging the new UPS.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | RGT2 Server inside Control Building | PMT and DERMAGA has discussed and reviewed the above situation. There is a need to engage with RGT2 Operation team for further understanding of RGTSU server power supply.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Electrical | RGT2 Server inside Control Building | To request ABT to engage with RGT2 Operation for 25 February site visit. However the sute visit date need to be confirmed by ABT.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Power and Instrument Cables | Identify all affected existing cables and also identify new replacement power and instrument cables routings.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Power and Instrument Cables | Cut/remove old cables whichever are possible, and mark them as unused cables, if cannot be removed,
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Multi Cable Transit (MCT) | Use existing MCT and if insufficuent, to perform coring for remaining new cable entries.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Lightning pole | To verify first and if there is a need than relocate the poles temporarily.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Lightning pole | To install lightning early detector for workers' safety.
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Instrument | Lightning pole | Grounding need to be verified for all instrumentation equipment (for equipment protection).
TANGGA BATU METERING STATION UPGRADING (ROCKS) PROJECT | FIP | Onshore - Others | Others | SOCSO requirements | According to SOCSO requirements, all permanent and temporary workers shall contribute to SOCSO.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Access to Elevated Cable Trays | Mark up the affected cable trays in the drawings after erection of scaffolding (1 month before work)
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Replacement of Brackets and Supports for Junction Box and Field Instruments | To verify supports and brackets of junction box for identification, touch up and replacement
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Aditional Scope of Work for Sedia Teguh | Need to know the cutoff date for placement of PO from MRCSB to Sedia Teguh for additional scope of work to this package by 28 May in order for timely completion.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Replacement of Brackets and Supports for Junction Box and Field Instruments | Need to mention which brackets need to be replace or reuse
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Replacement of Brackets and Supports for Junction Box and Field Instruments | Need to set the criteria for replacing cable trays and brackets for instrument.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Corrosion of Cable Trays | To put rubber mat between gulvanized cable trays and stainless steel cable trays in order to avoid surface touching
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Dismantling and Installing of Existing and New System Cabinets | To erect temporary extension platform in order to lift the cabinet at the stock piler area
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Dismantling and Installing of Existing and New System Cabinets | Methodolgy for cabinet dismantling at this stock piler area.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Dismantling and Installing of Existing and New System Cabinets | Lifting plan need to be establish for forklift and crane.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Dismantling and Installing of Existing and New System Cabinets | Contractor will come up with coordinated installation schedule for coke sulphur, stock piler stock piling by 17 June.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Working Space Constraints inside SCR 1, 3, 4 & 5 | Establish coordinated schedule for working in all SCRs including PCDM works.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Disposal of Dismantled System Panels | Need to liaise with ADC for disposal of panels.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Disposal of Dismantled System Panels | PMT to verify all temporary disposal area and applicable for other packages.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | Installation of UPS | To identify locations for UPS in all affected SCRs.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Aditional Scope of Work for Sedia Teguh | To conduct installation/construction review for the UPS and panels installation.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Loop Test Inspection and Verification | To establish loop tests schedule in order to optimized MRCSB manpower.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Logistics Plan | Logistics plan to be re looked due to new allocated laydown area proposal (near to area 5).
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Logistics Plan | Contractor to discuss with MRCSB on their proposal for temporary storage area for SCR works (ST want one close to SCR 3, 2 cabin with canopy need to discuss, 2 nos of cabin will be at RESET common area and canopy in front of cabin.)
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Logistics Plan | PMT to discuss with TA and area owner to place all cabins with gen-set at the proposed areas
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | Power Supply for New Controllers | Power cable jointing need to be verified and approved by PMT and MRCSB.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | Power Supply for New Controllers | Cable extension need to included in MOC
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Remove swing doors for all panels during pre-TA/TA for better access to work on the panels
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Need a mediator from PMT to supervise the coordination work among other contractors within SCRs
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Raised floor re-installation need to be done by raised floor specialist
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Need to verify whether the existing cable need to be removed or remains based on difficulty of removing cables
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Congested Area within SCRs | Work sequence and work coordination between stakeholders need to be established
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | Air-conditioned laydown area is needed for storing panels upon opening the timber crates and wrappings
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | Logistics plan need to be established on material transportation
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | Operation room can be use as storage room, subject to discussion and approval with OPERATION.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | Temporary storage plan to be discussed on 10/11 June
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Temporary Storage Area for Panels | To check TA Logsitics Plan whether have cabin or not around MCB
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Manpower Access | It is recommended to use the main access entrance for Honeywell. Proposal will be submitted to MRCSB for review and approval
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Manpower Access | The above not possible. Update - Honeywell to follow TA Logistic plan i.e. access through Gate 6
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Working until Extended Hours | RESET to propose and approve on the possibility of abolishing PTW renewals for working extended hours to MRCSB.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Working until Extended Hours | Update - MRCSB HSE come out with improvised PTW Management system i.e. extended 7 days
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Existing Raised Floor Panels | Reinstatement procedure for raised floor panels need to be establish
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Asset Disposal | PMT to verify all temporary disposal area and applicable for other packages.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Asset Disposal | MRCSB to follow up with Asset Disposal Committee (ADC) on the asset disposal procedure and approval
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Work Pack 22 (replacement of transmitters) | Work execution flow is required to be established due to large no. of transmitters involved.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Work Pack 22 (replacement of transmitters) | Leak checks are required to be done before gas-in, however this can be either waivered or to conduct random check on highest pressure pipings. PMT to follow up.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Work Pack 22 (replacement of transmitters) | It is proposed to conduct inspection of transmitters at Contractor's (Hyperwave) warehouse.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | Work Pack 22 (replacement of transmitters) | PMT to check whether these transmitters are tax exempted or not, which will affect on transmitters storage outside MRCSB area (bonded area).
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Electrical | WP 30 (lightning arrestor) | It is proposed to use sky lift for the work (60 meters height)
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Instrument | WP 21A (Shutdown valve) | To integrate with DELIMA.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Equipment Lifting and Preparation | To meet with area owners for crane arrangement during lifting area by area.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Equipment Lifting and Preparation | Both equipment and piping will be blinded using carbon steel plate (as per MRCSB standard procedure)
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Plot Plan, Layout & Heavy Lift | Equipment Lifting and Preparation | To check on the availability of lifting lugs/trunnions of the vessels prior to lifting
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Static Equipment | Condition of Existing Equipment Holding Down Bolts and Nuts | Physical verifications of the vessels and bolt and nuts need to done.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Static Equipment | Condition of Existing Equipment Holding Down Bolts and Nuts | If possible, (subjected to Operation approval) each of the nuts need to be loosen and greased to ensure easy and fast removal during the short TA period.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Static Equipment | Condition of Existing Equipment Holding Down Bolts and Nuts | Pending submission of all site survey reports on 14 June
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Condition of Existing Equipment Holding Down Bolts and Nuts | Interfacing with other contractors need to be done
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Condition of Existing Equipment Holding Down Bolts and Nuts | Progresssive discussion on TA integration meeting area by area, area 4 finished to discuss on work coordination on that specific area.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Identify all personnel that will be working for Dominant in order to go trainings organized by MRCSB.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Org chart for Dominant need to be submitted by Friday 31 May
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | Engineering personnel to be consider to be on site as Engineering Rep during TA for quick response
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | PMT to register Dominant as one of the Contractor to enter from Gate 6 for faster/easy access to the site.
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Others | Contractor's Manpower | HSE Safety Notice (MRCSB HSE requirements during TA) to the workers will be done after Raya
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | WHP and CPP fabrication area | Fabrication of CPP jacket will be in phases (box-up) will be installed upon top panel lfiting of WHP jacket completed, targetted in Dec 2021
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Delay of BOKOR CPP loadout affects WHP jacket construction | Fabrication of WHP jacket to be priotized and align with Bokor CPP loadout
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Delay of BOKOR CPP loadout affects WHP jacket construction | To have interface with Bokor CPP PMT
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Plot Plan, Layout & Heavy Lift | Flooding at fabrication no4 and no5 | Currently, plate provided as a temporary measure. Permanent solution shall be proposed by MMHE to improve water flooding issue for Kasawari project
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Skidded equipment | To further study on which braces to be put on hold to provide access for equipment skidding once upper deck has been installed
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Skidded equipment | To identify which equipment that may be affected to the process of skidding
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Skidded equipment | To check on the height clearance for equipment skidding
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Dimensional Control for critical points between topside and jacket | To ensure the dimensional control are being verified by PETRONAS Geomatics team
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Gap during inspection | To consider space and access for inspection during Detailed Design
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Availability of Vendor data for Instrument panel | To ensure VDI incorporated in drawing and develop installation method
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Availability of Vendor data for Instrument panel | To update material handling study based on latest VDI input
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Fixture quantities differ between architectual and electrical engineering drawings | To ensure no discrepancy and correct MTO issue prior to procurement
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Civil, Structure & Building | Strength jack support beam | To ensure location is clash-free
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Transportation plan availability | To award by end of December and plan to be made available ASAP
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Soil Investigation for WHP topside | To be completed by early January 2020 before 1st cut
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Interface between Contractor and Vendor | To expedite award of equipment and VDI by Vendor
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Contigency for material | To ensure correct IFC is produced and verify during mark-and-cut of the material
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Contigency for material | Contractor to consider contigency plan (ex stock material availability) for specific material
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Stiffner in Launch Craddle | To have further discussion and review
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Alignment of skid beam | Acceptance criteria to be established and agreed with Drilling team
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Alignment of skid beam | Offshore fabrication tolerance to be included in workpack
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Construction sequence | To relook the construction sequence (i.e. column insert after cellar deck installtion) and reflect in the manpower planning and schedule
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Interface with OIC | To get company installation representatives involvement during interfacing meeting
KASAWARI DEV. PROJECT (KSDP-A WHP) | Greenfield | Offshore - WHP | Others | Fabrication Engineering requirement | Joint review of BOCAD, markup drawing during Detailed Design
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Contractors | To establish the transportation route/plan for manpower & machineries and to propose to GPS ALT for approval
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Common Facilities Management | To seek approval from GPS ALT to use the Turn Around Village as the Project Temporary Facilities Area including equipment & material laydown (cable drum, pipe spool) and worker's temporary shelter to be included in the 80x90 working plot.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Others | Permit To Work (PTW) Issuance | All identified RA shall undergo e-PTW training organized by GPS.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Critical Equipment | To confirm on the height of the existing piperack. After reviewing the dwg the min height of the piperack road crossing is 6.0m
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Critical Equipment | To confirm the stack height during Detail Eng.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Critical Equipment | EPCC contractor to study on the lifting plan
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Accessibility for Critical Equipment | To seek potential vendor on the logistic and construction sequence
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Existing underground facilities | PE to issue work order on provision to perform underground detection & mapping
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Existing underground facilities | Civil to submit SOW complete attachment & cost estimate by end April 2019
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Soil bearing capacity & ground level contour | PE to issue work order on provision to perform soil investigation & topography survey
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Soil bearing capacity & ground level contour | Civil to submit SOW complete attachment & cost estimate by end April 2019
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Underground Scanning at Existing Plant Area | To confirm by manual excavation
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Underground Scanning at Existing Plant Area | To establish work scope for underground scanning at existing area (42" tie in foundation). To engage with Civil Team on the possibility in conducting underground scanning and manual excavation in order to confirm the facilities
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Underground Scanning at Existing Plant Area | To clarify with the potential bidders for AGO tie-in contract wether the scope of scanning & physical verification are included.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Additional Weight on Existing Raised Floor | To confirm on the capacity of raised floor to cater the additional DB, otherwise a separate steel structure frame is needed to support the DB.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Space Constraint for New Pipe Support | The design should take into consideration and verify the undeground facilities (scanning and physical verification) for the new pipe rack and pipe support.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Fire Proofing | To verify the basis of fire proofing of the new structure of the project and subsequently provide if required
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Static Equipment | Supporting Facilities for Equipment Delivery | Selection criteria - to identify and detail out on the available logistic facilities around the area to be included in ITB
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Static Equipment | Lifting Plan | To confirm on the equipment weight for lifting plan
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Static Equipment | Lifting Plan | Lifting study to be done to identify the space for the crane position. Also to verify crane location ground condition. All this information will be included in the ITB
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | New Fire Monitor & Hydrant | Process Safety to advice on the new location and to do outside Turn Around window
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | New Fire Monitor & Hydrant | To be confirmed with area owner (ABT- Area Based Team) for the execution
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | New Fire Monitor & Hydrant | To establish construction method of installing the new fire hydrant and monitor
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | Pipe Pressure Drop at New 42" Piping | To perform preliminary hydraulic calculation - to see the pressure drop for the 42" pipe. (Udpate: it was confirmed that the Pressure drop of 0.003 bar for 90m pipe length and it is acceptable)
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Piping | Pipe Pressure Drop at New 42" Piping | During detail design, EPCC contractor will check and verify the pressure drop (scope to be included in the ITB).
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Electrical | Verification of Existing Cable Trench | Separate contract will be awarded this month expect to start work by June 19
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Instrument | Instrument Cable Route | To confirm on the Instrument cable route wether it will use the same new pipe rack.
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Source of Temporary Water Supply | To seek Operation approval to use the plant service water for construction and to be mentioned in the ITB
ACID GAS OXIDIZER (AGO) PROJECT | FIP | Onshore - Production | Temporary Facilities | Source of Temporary Power Supply | To seek Operation approval to use the plant power supply(for welding work etc) during construction
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Crossing/Transporting of Equipment below Pipe Rack Structure | Include in BEPCC ITB for Contractor to study other possible hauling/route options.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Limited Access and Working Area for HRSG | To identify possible access for HRSG1 replacement works and to be inlcuded in the BEPCC ITB.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Limited Access and Working Area for HRSG | Contractor is to proposed a lifting plan for replacement of HRSG1 and also to include all other equipment's lifting, and this requirement is to be included in BEPCC ITB.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Facilities | GDC KLIA to seek assistance from Malaysian Airport Berhad (MAB) to allow placement of Contractor's temporary facilities near to project site.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Facilities | The temporary facilities requirements need to be included in BEPCC ITB.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Demolition Work | Survey for new equipment location and soil investigation need to be conducted to verify soil parameters and to identify existing facilities.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Demolition Work | To isolate existing demolished facilities from its surrounding.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | AGB Boilers Access | To dismantle existing AGB boilers parts by parts and assemble new AGB boilers parts by parts also.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | AGB Boilers Access | Possibility use of forklift to transport existing and new AGB boilers to the main building and to be included in BEPCC ITB.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Relocation of Existing Facilities | Identification of these facilities that need to be temporary relocated will be done during BED.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Modification of Existing Pipe Racks and Pipe Support Foundation (new foundation / modification of existing foundation) | To carry structural asessment on the existing pipe racks/supports.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Modification of Existing Pipe Racks and Pipe Support Foundation (new foundation / modification of existing foundation) | To establish blinding plan for pipe isolation (for tie-in works).
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Permit to Work (PTW) | PMT to engage with GDC Operation to establish PTW Application and Approval Plan which will be included in BEPCC ITB.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Temporary Facilities | Requirement of utilities utilization (e.g electricity, water, instrument) during Construction and Commisioning | Include the scope of supply in BEPCC scope.
GDC KLIA HRSG and AGB Boilers PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Height Restriction for Outdoor Lifting | To engage with Department of Civil Aviation (DCA) on the height limit for lifting activities due to its flight path requirements and to be included in BEPCC ITB.
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | To get dedicated AA for PTW application
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | To initiate interface meeting with asset owners
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Access to Project Site | PMT to engage with TA team to highlight on MLNG SOx Project construction activities
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Project Site Platform Elevation | To perform survey
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Project Site Platform Elevation | To carry out soil investigation and come out with earthwork proposal in order to determine the project platform level
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heat Radiation from Nearby Slug Catcher Flare (A6331AB) | MLNG to share heat radiation contour for the nearby slug catcher
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heat Radiation from Nearby Slug Catcher Flare (A6331AB) | Cross reference to HAZID Category 1, item 6.3.1)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Construction Near to the Trunk Line including LNG Rundown Line | To carry out underground scanning including pilot holes after confirming equipment layout
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Construction Near to the Trunk Line including LNG Rundown Line | PMT to organize multiple engagement with SK Gas for information and MLNG team for approval
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Lift and Soil Condition | To carry out soil investigation
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Shallow Ground Water Level | To carry out soil investigation and to establish current water level
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Civil, Structure & Building | Shallow Ground Water Level | To determine the correct construction method
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Seawater Discharge Pipe from Aeration Basin | The seawater discharge system from the aeration basin (open channel or approximately 1 km away) will be finalized at the end of FEL 2 by Seawater DFS Engineering Team
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Verification of Existing Firewater Ring | Further firewater requirement study will be done during FEL 3 and necessary upgrading will be incorporated in FEL 3 study
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Pipe Routing for New Acid Gas Line for MLNG DUA and MLNG TIGA including BF Water, HP Steam and Utilities | Site visit and line tracing will be done next week between MLNG and PMT
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Pipe Routing for New Acid Gas Line for MLNG DUA and MLNG TIGA including BF Water, HP Steam and Utilities | Cross reference with HAZID Category 2, item no 7.1.1
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Piping | Non-Metallic Pipe for Sour Gas Line | Further study will be mde during FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Electrical | Existing Underground Cables at Project Site (including instrument cables) | Underground scanning, verification with drawings, and pilot holes will be done during FEL 3 (to be included FEL 3 SOW)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Electrical | Existing Underground Cables at Project Site (including instrument cables) | Pilot holes for cable trench space availability verification from substation 66 will be done during FEL 3 (to be included FEL 3 SOW)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Instrument | Instrument Tie In to Main Field Station (MFS) / MPCC | To further study during FEL 3 (to be included in FEL 3 SOW)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Laydown and Temporary Rest Area Location | PMT to engage with SK Gas on the use of SK Gas area as temporary facilities area
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Laydown and Temporary Rest Area Location | Laydown area to be identified and approved in FEL 3 (to be included in FEL 3 SOW)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Laydown and Temporary Rest Area Location | To explore other areas (e.g former Train 9 laydown area) as MLNG SOx temporary facilities area if SK Gas area is not feasible
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Manpower Transportation from TIGA Main Gate to Project Site | PMT to engage with Facility Management Administration on the requirements
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Equipment Transportation | To further study equipment transportation in FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Utilities Supply for Construction | Temporary utilities supply for construction will be determined during FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Temporary Utilities Supply for Construction | PMT to engage with MLNG Utility Head on the temporary utilities supply
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Waste Disposal Plan (i.e. Construction Waste, Scheduled Waste, Domestic Waste) | PMT to explore using existing MLNG waste disposal management
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Temporary Facilities | Waste Disposal Plan (i.e. Construction Waste, Scheduled Waste, Domestic Waste) | PMT to engage with MLNG HSE on the temporary waste disposal area / method (to e included in FEL 3/EPCC SOW)
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Preservation of Equipment upon Arrival on Site | The requirements for equipment preservation will be defined in FEL 3 and to establish preservation plan during EPCC
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Availability of Skilled Manpower Nearby | Cross reference with HAZID Category 2, item 1.1.1.
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Interface with MLNG Electrification Project | PMT to engage with MLNG Electrification and MLNG NOx projects on their construction schedule and optimize the schedules with MLNG SOx Reduction Project
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Monsoon and Haze Season (High Tide) | To indicate monsoon/haze plan requirements in the EPCC ITB for the contractor to propose
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Monsoon and Haze Season (High Tide) | To identify the period of monsoon/haze season
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Monsoon and Haze Season (High Tide) | Cross reference to HAZID Category 1, item no 2.8.1
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Tie-Ins (BF Water, HP Steam, Utilities) | Refer to item CR01:P02
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Integration between Main Contractor and Licensors | Interfaces with licensors and vendors of all concurrent projects in MLNG will be included in the main contractor SOW
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Custom Clearance | PMT to engage with Train 9 New MRU PMT on the custom clearance approach and tax exemption
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Authority Approval to Start Work (e.g. DOSH) | To include in EPCC ITB, liaise with all relevent authorities in order to commence physical site activities timely
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Delivery Schedule for Equipment | To be done in FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | eMOC Management | PMT to specify the scopes for tie-ins to the existing facilities with expected changes to allow registration in MLNG eMOC for subsequent actions
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Packaged Unit | Packaged Equipment Transportation Warranty | To be included in the EPCC SOW
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Demolition / Isolation of Existing Equipment | To further study during FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Special Tools Requirements | To include in EPCC ITB the requirement of special tools and further review during FEL 3
MLNG SOx REDUCTION PROJECT | FIP | Onshore - Production | Others | Valid Sarawak Work Permit (EPCC, PMT and FEL 3 Team) | The requirements of valid Sarawak work permit to be included in EPCC SOW
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | River and Railway Crossing for Pipelines | To identify relevent authorities
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | River and Railway Crossing for Pipelines | To engage with relevent authorities for crossing approval
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | To conduct U/G scanning at the existing auxilary boiler foundation to identify all underground facilities
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | To perform study on using the existing auxilary boiler foundation for the new boiler
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | To conduct lifting study of new boiler facilities and to consider modular-type of boiler
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Option B Boiler Location | To consider utilizing the existing plot area by optimizing the new boiler equipment layout and to engage boiler vendor in the next stage
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Height and Width Clearance within UK for Logistic Purpose | To engage with UK team on the maximum height and width clearance for equipment delivery and crane access within UK
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Land Acquisition for External Pipeline Area including Access | Upon obtaining all the information, it will be included in EPCC ITB
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Brownfield and Greenfield Demarcation | To identify all 4 brownfield areas clearly for different permit application processes
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Brownfield and Greenfield Demarcation | Interface and engage with 4 diffferent area owners
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Civil, Structure & Building | Existing Pipe Racks and sleepers | Construction execution need to consider new pipe racks and sleepers to cater for new pipings and facilities
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Civil, Structure & Building | Existing Pipe Racks and sleepers | To engage with all existing pipe racks and sleepers Owners on using the existing pipe racks and sleepers for new pipings and facilities
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Civil, Structure & Building | Existing Pipe Racks and sleepers | These information will be included in the EPCC ITB
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Obstruction at new AFC Area | To engage with Owner on relocation of the existing valve from the AFC area
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Obstruction at new AFC Area | To include the relocation of existing valve study in Detailed Feasibility Study (DFS)
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Valves Passing | To conduct physical verification on the valve passing for all services
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Valves Passing | Further study will be conducted if the valves were found passing
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Piping | Code Demarcation for External Pipings (Pipeline) | Code demarcation for external pipings to be discussed and finalized with KTSB
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing Electrical and Instrument Cables in UK | To reconfirm on the availability of As-Built Drawings for all cable trench at proposed project site in UK
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing Electrical and Instrument Cables in UK | To conduct U/G scanning in next phase of work
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing Electrical and Instrument Cables in UK | To study the possibility of A/G cable routing
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing 33kV GIS Switch Gear | To verify with Owner on the condition of the spare circuit breaker is maintained or serviced (obtain maintenance record of the circuit breaker)
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Electrical | Existing 33kV GIS Switch Gear | To include project work scope if the circuit breaker was not maintained or serviced
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Instrument | Modification of Instrument Facility at UK Control Room | To check and verify the cables arrangement under the raised floor in UK Control Room
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Temporary Facilities | Laydown Area | To identify the laydown area and temporary facilities (utilities, site office, etc.) within UK
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Project Execution during Operation (SIMOP) | To engage with Owner on the list of works that will be done when plant is in operation
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Project Execution during Operation (SIMOP) | To establish Project Execution Plan considering SIMOP including Boiler, Boiler Feed Water and Air-Fin Cooler Installation Sequence
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Project Execution during Operation (SIMOP) | To conduct engagement session with Operation before construction works begin
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Project Execution during Operation (SIMOP) | These requirements will be included in EPCC ITB
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Tie-In Points at DMC Plant | To engage with DMC on the finalized coordinate of tie-ins at DMC Plant in order to update tie-in points accordingly
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Tie-In Points at DMC Plant | This information will be included in EPCC ITB
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Tie-In Points at DMC Plant | PGB Business team to come up with agreement for power and utilities at DMC
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | EIA Requirements | To engage HSE on the EIA execution proposal of conducting environmental assessment
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | EIA Requirements | To engage DOE on the best option on how to provide EIA for this project
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | EIA Requirements | To identify all regulatory permits requirements
PGB DMC PROJECT | Plant Change | Onshore - Petrochemical | Others | Overall Project Schedule | To develop overall project schedule based on the utilities and feedstock requirement dates by DMC
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To conduct further logistic study by FEED Contractors during FEED on land transportation access to the project site.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To identify bulk equipment or material for each mode of transportation land or sea frieght
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Limited Site Accessibility (Material and Equipment) | To include the reinstatement of damaged facilities to be borne by Contractor (EPCC scope).
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | To find out any future projects around project site vicinity and Sabah Oil and Gas Industrial Park (SOGIP) area and SAMUR turnaround activites
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Heavy Traffic during Construction Phase | To include in ITB for potential Contractor to find out for best option for accommodation and access road to avoid traffic congestion during construction.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To verify the integrity of existing facilities by FEED Contractors and obtain permission from Facility Owner (to be included in FEED ITB) to cater for worst case scenario of 3.0 MTPA.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To explore options of constructing new MOLF to cater for the worst case scenario.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To provide temporary power supply during construction phase.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To explore and verify temporary power and water supply from adjacent SAMUR plant.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | Identify and verify adequate water supply for construction activity (for hydrotesting and flushing).
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Utilizing Existing Facilities (i.e. MOLF, temporary facilities, plant road, temporary power) | To consider access road during emergency response and to interface with SOGIP and SAMUR.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | To identify the dedicated stakeholder personnel for PMT and EPCC org chart to liaise with SOGIP on fabrication and laydown areas.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | PMT to initiate discussion with authorities and establishes project specific approval work process on fabrication laydown area to minimize schedule impact if indeed additional space is required
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Fabrication and Laydown Areas | To identify additional area for shutdown (shutdown village) and to be included in site preparation work and to be included in FEED SOW.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | To include the construction camp requirements (including authorities, etc.) in the FEED ITB.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | PMT to survey accommodation availability around Sipitang.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Construction Camp / Workers Accommodation not Completed in Time | PMT to establish with HRM on reallocation package for the PMT personnel (to be finalised and approved before 1st site mobilization)
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Vehicle Refuelling for Industrial Usage | To put under EPCC scope to provide refuelling station for industrial use and dictate that only PETRONAS fuel and lubricant can be used. To be specified in Contruction Execution Plan (CEP) during FEED.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | To verify the availability of required heavy lift equipment in EPCC scope.
PROJECT Z | Brownfield | Onshore - Production | Temporary Facilities | Availability of Heavy Lift Equipment | PMT to provide Group Procurement (GP) crane suppliers in the project site area to EPCC Contractor. This information to be included in ITB EPCC
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | EPCC Contractors to engage with skilled workers from outside Sabah.
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | EPCC Contractor to identify SOW that can be undertaken by Sabahan workers and SOW cannot be undertaken by Sabahan workers (skilled and semi-skilled works).
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Local Skilled Manpower (including vendor) | PMT to liaise with Sabah State (Human Resource Ministry) and Immigration Office to understand Sabah requirements for employing non-Sabahan workers.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | FEED Contractor to carry out assessment on the best method for piling without affecting adjacent plant operation.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | EPCC Contractor to conduct survey prior to construction activities to establish baseline of existing facilities conditions.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | Damages to the adjacent PCFSSB plant caused by Project Z activities need to be rectified by EPCC Contractor.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Interruption to Existing Plant (PCFSSB) i.e piling, marine traffic | To conduct marine traffic risk assessment (MTRA) to simulate nos of marine vessels during Project Z construction phase against current PCFSSB marine traffic (including local fishermen and SFI activities).
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To separate workers camp / accommodation to different ethnic and nationality.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To establish fence and security for materials and equipment storage laydown area. and warehouse.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | EPCC Contractor to liaise with PETRONAS Security and Sabah Police on support for surveillance of materials and equipment storage laydown area nad warehouse.
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | To establish security system for foreign workers
PROJECT Z | Brownfield | Onshore - Production | Others | Security Issue (theft, manpower control) | PMT to engage with State Police and PETRONAS Security Head on security matters of Project Z during project execution.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | To include in EPCC Scope of Work as part of EPCC Contractor responsibility to train local Sabah Contractor to familiar and comply with PETRONAS HSE requirement.
PROJECT Z | Brownfield | Onshore - Production | Others | HSE Requirement for Project (Common) | To develop HSE procedure for Project Z based on either greenfield or brownfield project (Note: Considering SAMUR plant is nearby, not sure full greenfield project could be implemented,e.g Train 9 project declared as Greenfield)
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | To establish Project Regulatory Approval Matrix to cover for local law and regulations, government regulations and statutory approvals (by FEED Contractors).
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | PD&T HR to assist on planning for work permit application for PMT.
PROJECT Z | Brownfield | Onshore - Production | Others | Enforcement of Foreign Manpower by Local Authorities Working Permit Restriction for non-Sabahan Workers | To identify the dedicated stakeholder personnel for PMT and EPCC org chart to cater for working permit application and management.
PROJECT Z | Brownfield | Onshore - Production | Others | Weather and Sea Condition with respect to Construction and Transportation | EPCC Contractor to study te local weather condition and take into consideration in their Construction Execution Plan (CEP) i.e. Monsoon Season Plan.
PROJECT Z | Brownfield | Onshore - Production | Others | Nearby Local Resident Disturbance | Engagement with local community to be conducted through SOGDC.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | To perform EIA study.
PROJECT Z | Brownfield | Onshore - Production | Others | Dredging Activities | PMT to check with Sabah Port and Jabatan Laut on the requirement of dredging contractor in Sabah marine area.
PROJECT Z | Brownfield | Onshore - Production | Others | Local Authorities Requirement on Marine Transportation and MOLF | To engage with Sabah Port and Jabatan Laut in order to understand Local Authority requirement on marine transportation and MOLF
PROJECT Z | Brownfield | Onshore - Production | Others | Interfacing with Concurrent Construction Activities (pipeline, jetty) | EPCC Contractor as a single party to coordinate and manage multiple subcontractors and clear demarcation of SOW between the subcontractors and to be included in CEP.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | To establish SIMOP Plan during detailed engineering.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | Systemization Plan to be establish during early stage of detailed engineering.
PROJECT Z | Brownfield | Onshore - Production | Others | Concurrent Construction and Commissioning Activities | To specify the requirement of systemization execution during 60%-70% of construction progress in EPCC SOW.
PROJECT Z | Brownfield | Onshore - Production | Others | Pinching and Lost of Manpower due to Nearby Major Projects | To include the manpower control during construction in the CEP which include body pass system for head count and productivity tracking purposes.
PROJECT Z | Brownfield | Onshore - Production | Others | Congestion during Peak Construction Activities | FEED contractor to provide details of construction strategy in Construction Execution Plan (CEP) to ensure safe working environment during peak construction period
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Bulk Construction Materials (sand, cement) | EPCC Contractor to include the source of bulk construction materials in CEP
PROJECT Z | Brownfield | Onshore - Production | Others | Availability of Bulk Construction Materials (sand, cement) | To identify potential supplier for bulk construction materials during FEED.
PROJECT Z | Brownfield | Onshore - Production | Others | Subcontractor Selection | EPCC contractor to produce subcontractor selection process under Procurement Procedure for PMT approval.
PROJECT Z | Brownfield | Onshore - Production | Others | Subcontractor Selection | Subcontractor evaluation procedure to be established by EPCC Contractor to be reviewed and approved by owner.
PROJECT Z | Brownfield | Onshore - Production | Others | Contractor and Subcontractor Productivity | Extended working hours
PROJECT Z | Brownfield | Onshore - Production | Others | Contractor and Subcontractor Productivity | Similar to item CR01:TF06.
PROJECT Z | Brownfield | Onshore - Production | Others | Utilization of Gas Turbine from MLNG to Project Site | To present the case to Project Steering Committee for direction.
PROJECT Z | Brownfield | Onshore - Production | Others | Early Site Posession | PMT to formally secure the proposed plot for Project Z from SOGDC by November 2019.
PROJECT Z | Brownfield | Onshore - Production | Plot Plan, Layout & Heavy Lift | Plot Plan Optimization | FEED QRA study to take into consideration PCFSSB and expansion phase. FEED Constractor to design the Project Z plot plan incompliance with QRA report.
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Single Lift vs Multiple Lifts | PMT to study Cost Benefit Analysis (CBA) between single lift vs multiple lift options
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Single Lift vs Multiple Lifts | PMT to identify the min clearance required from existing facilities for heavy liftings
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Vessel Crane Availability | PMT to finalize the crane capacity that will be used for heavy lifts
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Vessel Crane Availability | Based on item 1, PMT to decide whether to use Hook Up or Installation contractors
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Vessel Crane Availability | PMT to plan the contracting strategy for 2021
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Vessel Crane Availability | PMT to check with MPM/GP on the vessel availability
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Mooring Line of Vessel | MIE to check on structural integrity for soft mooring
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Anchor Pattern of Vessel | PMT to conduct anchor pattern study
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Heavy Lifting Sequence | ssue 1 to be decided first before Action Item 2 can be done during DED
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Heavy Lifting Sequence | A detailed Heavy Lifting Plan and Analysis to be developed
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Plot Plan, Layout & Heavy Lift | Heavy Lifting Sequence | Assumption on the vessel and crane to be used (CAT1 Barge & exact layout and specs) to be determined
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Additional Load on Existing Structure | Install ability study shall be conducted on the best way forward to install the deck extension.
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Offshore Structure Welding Activities | To determine nos of offshore welds to be performed at site
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Civil, Structure & Building | Support and Bracing Requirements | MIE to provide detailed calculation for the bracing requirements on the selected option (either single lift or multiple lift)
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Static Equipment | Installation of Static Equipments | PMT to carry out Cost Benefit Analysis (CBA) on the static equipment installation
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Pipe Routing | MIE to finalized the pipe routing based on the selected option (single lift or multiple lift)
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Tie-In Points | To determine the nos of tie-in points and methodolgy for shutdown
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Tie-In Points | MIE to check on the integrity of the tie-in points
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Piping | Tie-In Points | To determine whether there is a need for hot tapping
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Turn-Around | To discuss with Operation on the details of TA duration
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Overall Contracting Strategy (OCS) | PMT to determine whether to use Installation, Hook Up or EPCIC type of contract
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Overall Project Schedule | PMT to develop overall project schedule
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | PMT Org Chart | PMT Org Chart for all project phases need to be developed
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Offshroe Installation of Deck Extension | The approval whether single lift or multiple lift will be done is to be decided by PMT FEL3
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Congested work during TA | PMT to interface with Operation and Maintenance teams on integrating works during TA
M1 Produced Water Treatment System (PWTS) PROJECT | Brownfield | Offshore - CPP | Others | Congested work during TA | PMT to register all activities during 2021 TA with Operation
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To check the space adequacy for the installation of the heavy lift crane
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To carry out soil investigation at proposed crane location
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | Route survey need to be carry out from Labuan Port to PCML 2 for land transportation and from the sea to PCML 2 for sea transportation
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To engage specialist on heavy lifting for verification
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To verify the weight of the boiler module and the boiler assembly upon confirmation of construction and installation strategy
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To look into relocation of firewater tank and pump skid due to possible obstruction if the boiler is transported via sea
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Access for Material / Equipment (Crane, Boiler, etc.) | To include in EPCC ITB the requirements for Contractor to engage with Forwarders
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Heavy Lift' Crane Availability | To source the high-capacity crane upon verification of boiler's weight and size
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Heavy Lift' Crane Availability | To identify potential heavy lift contractors
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Heavy Lift' Crane Availability | To consider other methods of installation (e.g. using dual axle SPMT)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Unknown Soil Condition to support Heavy Lift Activities and MOLF | To conduct soil investigation for both onshore and offshore locations
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Unknown Soil Condition to support Heavy Lift Activities and MOLF | To conduct offshore survey for MOLF
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Construction of Material Off Loading Facilities (MOLF) | To conduct detailed feasibility study for MOLF requirements
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Plot Plan, Layout & Heavy Lift | Construction of Material Off Loading Facilities (MOLF) | To engage with local authorities and regulatory to establish regulatory requirements
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Civil, Structure & Building | Underground Facilities | To obtain underground facilities drawings at project site area
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Civil, Structure & Building | Underground Facilities | Owner to conduct internal underground scanning during FEED to verify as-built drawings of the project site and the underground scanning report to be included in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Civil, Structure & Building | Underground Facilities | EPCC to conduct underground scanning and pilot holes to physically verify the underground scanning report from Owner
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Civil, Structure & Building | Underground Facilities | All parties involved need to conduct site verification before the endorsement of PTW
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Piping | Tie-In Points and Routing | To identify and verify the existing pipe supports and structures can withstand the additional pipes and cables (or erect new pipe rack structures)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Piping | Tie-In Points and Routing | To include all requirements in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | PMT / Owner to explore potential nearby land owner for availability and estimated cost
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | To explore the usage of TA canteen and toilet facilities before TA on the requirements and approval from Corporate Communication Administration (CCA)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Limited Laydown Area during TA | To identify external laydown area for SUMILAU project
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Limited Laydown Area during TA | To complete all construction activities excluding tie-ins outside of TA
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Temporary Facilities | Limited Laydown Area during TA | To establish proper demarcation of PTW approver (e.g. all tie-ins activities are under PCML and boiler works are under PMT)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Schedule Impact due to TA Date Change | Others | 1) Awaiting final decision on TA date for PCML Plant 2 to decide on the tie-in work strategy (when and who will execute tie-in activities)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Adverse Weather | Others | To be included unproductive days due to adverse weather in schedule planning
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Adverse Weather | Others | To obtain weather data from meteorological department
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Emergency Readiness Supporting Plant | Others | Owner to identify malfunction emergency readiness system and rectify them prior to project execution and vice versa
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Emergency Readiness Supporting Plant | Others | Any emergency readiness system still inoperative need to be informed to PMT
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Theft in Plant during TA | Others | EPCC to appoint security personnel at their battery limit area
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Theft in Plant during TA | Others | EPCC to explore laydown area outside plant and ensure the security of their materials
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Theft in Plant during TA | Others | EPCC to engage with PETRONAS Security on the project site security arrangement
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Theft in Plant during TA | Others | To verify requirements of engagement of third party security personnel working in project site
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Long Holiday Season | Others | To identify long holiday season during project execution with Contractor and propose mitigation plan to overcome loss of productivity
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Long Holiday Season | Others | To include long holiday season in schedule planning during project execution and ensure such plan is being considered by EPCC Contractor
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Low Performing Contractor/Vendor | Others | To establish stringent technical criteria for contractor/vendor selection
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Low Performing Contractor/Vendor | Others | To engage local authorities for requirements on employing skilled foreign workers
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Low Performing Contractor/Vendor | Others | Contractor to have minimum working experience in oil and gas brownfield area (more than 10 years) and have experience in installing boilers with own boiler installation license or to appoint licensed boiler installer
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Local Grievences | Others | To identify labor relation / liaison officers from both PMT and Contrctors, and this requirements to be included in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Local Grievences | Others | To establish labor relation committee comprising of PMT and Contractor plus Owner for managing all labor related issues
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Local Grievences | Others | To organize constant engagements with workers
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Local Grievences | Others | All the above need to be included in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | To have early engagement with Operation to establish the work plan for PTW approval
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | To engage with Plant Owner to identify dedicated AA for all PTWs
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Hot Work in a Live Plant & Confined Space | Others | To include in EPCC ITB the requirements for certified Authorised Gas Tester (AGT)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Concurrent Construction Activities by Different Contractors | Others | To organize interfacing meeting
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Lack of Resources during TA | Others | To engage with PETRONAS security on manpower control system among contractors to track manpower movement
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Lack of Resources during TA | Others | To explore dual access control system (ID and thumbprint) implementation and to include in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Lack of Resources during TA | Others | To consider redundancy of construction equipment and to remind the contractor on such situation, to remind contractor to secure all major construction equipment as early as possible
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Competency of Workers | Others | To reinforce the manpower competency requirements in the EPCC ITB and to consider as one of the evaluation criterias
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Competency of Workers | Others | To closely verify all competency certifications by respective disciplines and to establish approval process
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Special Material WPS | Others | To consider modular type of boiler to reduce field welding
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Special Material WPS | Others | To include the requirements of qualified welders in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Special Material WPS | Others | EPCC / JV partners to have boiler erection license (from DOSH) as pre-requisite to participate in the project
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Insufficient FEED Information | Others | Hydraulic study verification is ongoing with GTS
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Insufficient FEED Information | Others | Electrical load study report draft submitted by PCML and pending PMT review and comment
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Insufficient FEED Information | Others | To identify early electrical load requirements for new boiler facilities
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Insufficient FEED Information | Others | To establish clear demarcation scope matrix (e.g. RACI chart, etc.)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Boiler Vendor and EPCC Contractor SOW Dispute | Others | To conduct team building and synergy workshop among Contractor and Vendor and to be included in EPCC ITB
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Boiler Vendor and EPCC Contractor SOW Dispute | Others | To establish a steering committee comprising of Contractor and Owner
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Boiler Vendor and EPCC Contractor SOW Dispute | Others | PMT to engage with third party to manage Vendor's activities (still within Contractor's scope)
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Interface between PMT and Owner | Others | To establish communication channel and interface procedure
SUMILAU PROJECT | FIP | Onshore - Petrochemical | Interface between PMT and Owner | Others | To consider the implementation of LEAD program for HSE during execution
Refinery Asset Rejuvenation Tiga (RESET) PROJECT | Rejuvenation | Onshore - Refinery | Existing Raised Floor Panels | Instrument | Support base for furnitures need to be finalized (manpower, type of raised floor)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Requirements, Drawings, and Procedure | Sequencing of heavy vehicle/ transportation movement to be incorporated during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Requirements, Drawings, and Procedure | Proper sequencing during detailed engineering and IDC to be done during detail design phase to incorporated other disciplines' input into plot plan and civil drawings.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Underground Detection | Pilot digging to be proposed to supplement underground scanning proposed for SI SOW ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Underground Detection | Underground scanning to be part of SI SOW inside ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Coordination on detailed SOW between vendor and engineering consultant to be done once awarded
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | PMT Project Management team to clarify on the mode of execution for Titanium OSBL Project prior to imposing discipline engineering requirement
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | IDC to be done during detail design phase to incorporated other disciplines' input into civil drawings.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Study to be included as part of detail design engineering phase
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | PMT Project Management team to clarify on the mode of execution for Titanium OSBL Project prior to imposing discipline engineering requirement
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Site visit by PMT/ Construction team to be done prior to confirmation
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Interfacing scope/ study to be done during detailed engineering and to be parked under engineering consultant scope
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | To check with PIC Site Management team/ Common Facilities team on the status of existing TBM prior utilization for Titanium OSBL Project.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Interfacing scope/ study to be done during detailed engineering and to be parked under engineering consultant scope
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Civil Work | Owner/PRPC to be engaged for confirmation/ redline mark-up on existing tie-ins.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Engineering Interface | Change the contracting strategy to EPCC for the ETP package
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Civil, Structure & Building | Engineering Interface | Provide detail engineering on vendor package earlier to engineering consultant which in schedule need to engaged vendor earlier.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Lighting requirement based on lux calculation shall be incorporated inside vendor scope inside ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Detailed engineering and incorporation into MTO to be done during detail design phase
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | EX database to be provided during detailed design. Comprehensive EX requirement and inspection should be explained inside the scope of work of Package Contractor
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | MTO and material specification | Initial inspection to be performed by competent personnel during construction and before precommissioning work
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Cable | PMT Electrical engineering team to confirm cable routing and cable entry for new power cables based on existing redline markup drawings during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | Study on CP requirement to be done on ETP equipment
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | To confirm scoping of commissioning activities to prevent misalignment that may lead to CO.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | To propose for temporary main power usage throughout construction execution phase
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Execution | Requirement to be listed down and cascaded into Package Contractor SOW if necessary.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Engineering Interface | Change the contracting strategy to EPCC for the ETP package
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Electrical | Engineering Interface | Provide detail engineering on vendor package earlier to engineering consultant which in schedule need to engaged vendor earlier.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | To ensure 3D model review to focus on the assesibility, maintenance and operability for instrument field devices' locations
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | To identify critical activities within FAR 630 and provide proper mitigation measures. Migration downtime to be identified and discussed with Owner
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Most FOC to be AG except for certain part of the north due to no existing piperack. Spare UG conduit has been identified.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | PMT Electrical engineering team to confirm cable routing and cable entry for new power cables based on existing redline markup drawings during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | EPCM Contractor to be as focal for integrator between consultant and package contractor
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | IDC to be scrutinize during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | To identify critical activities within FAR 630 and provide proper mitigation measures.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Construction Execution for I&C | Migration downtime to be identified and discussed with Owner
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Instrument | Material Management | Requirement for warehousing and warehouse manning to be established
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | To confirm on the execution mode for Titanium OSBL project (brownfield/ greenfield) as well as best PTW system to be used
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | Establishment of Site Rules & Regulation Procedure
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | PTW | To confirm with PRPC Site Management on new/existing RCP guideline
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | To confirm with PRPC Site Management on communication and interface guideline
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | SIMOPS guideline to be provided to Package Contractor during detail engineering
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | To include provision inside the contract/ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | Energization guideline to be provided to Package Contractor during detail engineering
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | To scrutinize ORM (Operational Risk Management) and to adopt inside the contract if applicable
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | To check availability of permitting team in PIC
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | Plan to adopt AWP concept for construction execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | To check with SM on the availability for waste management contractor/ To check during site visit
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | To confirm with PRPC Site Management on tie-in condition and pre-requisite prior to execution of Titanium OSBL Project
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Systemization | Identify system and sub-systemization involved for pre-commissioning and commissioning planning to be adopted in construction schedule and sequence. (for both ETP & interconnecting)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | CSU | To confirm with PRPC Site Management on tie-in condition and pre-requisite for shutdown measure or alternative options prior to execution of Titanium OSBL Project
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | Detail fire fighting equipment to be established during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Project Communication and Interface | To confirm with PRPC Site Management on tie-in condition and pre-requisite prior to execution of Titanium OSBL Project
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Training | To check with CFS on availability of training centers
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Health, Safety, Security and Environment (HSSE) | Information to be transferred to responsible party for EMP update provided vendor data is received
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Training | To check with AMT contractor on maintenance training providers availability
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Blind list and isolation scope of work to be determined. To ensure associated work for each tie-in scope incorporated in PC scope such blinding/de-blinding, scaffolding, insulation, NDT etc if required to performed by PC contractor. (for both ETP and interconnecting scope)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Isolation requirement to be detailed out and parked under ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | To countercheck with Site Management on probable shutdown/ isolation for these 3 lines
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | Coordination meeting/ interface meeting to be done at the earliest convenience between PIC/ Plant Owner and Titanium OSBL team.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Tie-In | To confirm on total ETP tie-ins during detail design
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Insulation thickness to be considered during detailed engineering
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Specific schedule intended shall be addressed for each piping material as part of project control scope.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | Construction method/ training to be scrutinized to ensure proper execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | To discuss with area owner/plant owner (CR with Owner) on post-hydotest water removal allocation
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Engineering to gather existing piperack design calculation (CVS) and confirm whether it caters future expansion such as Titanium OSBL project piping lines
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Requirement and procedure to be developed during detail design phase
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | Process requirement during PTR to be elaborated as part of ITB issuance
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Fabrication, Testing and NDT | To discuss with area owner/plant owner (CR with Owner)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | MTO and material specification | PWHT requirement to be consolidated in detail under MPEI ITB SOW if necessary
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Piping Pre-qualification | To relook back on the requirement for 10 production joint considering fast-track nature and complexity of Titanium OSBL project.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Engineering Interface | Change the contracting strategy to EPCC for the ETP package
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Piping | Engineering Interface | Provide detail engineering on vendor package earlier to engineering consultant which in schedule need to engaged vendor earlier.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Scope of supply to be determined
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Vendor scope demarcation/interfacing to be identified including engineering, procurement, etc.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Vendor lesson learnt to be incorporated inside vendor ITB (Siti)
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Mechanical Rotating Equipment List | Vendor support to be incorporated inside vendor ITB
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Engineering Interface | Change the contracting strategy to EPCC for the ETP package
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Rotating | Engineering Interface | Provide detail engineering on vendor package earlier to engineering consultant which in schedule need to engaged vendor earlier.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Tank | To elaborate on vendor requirement inside ITB SOW as well as applying construction assisted engineering.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Tank | To discuss with area owner/plant owner (CR with Owner) on post-hydotest water removal allocation
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Static Unfired Item/ Vendor Package | Equipment space and height availabilty to be elaborated during detail design.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Static Unfired Item/ Vendor Package | IDC check to be done during detail design phase.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Static Equipment | Discipline Related Material | Titanium OSBL team to scrutinize the vendor package in detail as well as to be elaborated in detail within ITB SOW
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Location of TCF to consider distance with actual project location which will impact productivity. Site visit to be conducted.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | Nearest permanent utilities tie-in to be identified
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | PMT to check with CFS on SPC/ worker's camp availability
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | PMT to check with CFS on warehousing for sensitive equipment at central warehouse
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | PMT to check with CFS on existing Emergency response plan within PIC
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | To be determined during site visit
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Temporary Facilities | Temporary Facilities | To be parked under package contractor if necessary.
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | To be included inside freight forwarder roles and responsibility inside proposed contract with EPCM contractor
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | to be identified during site visit with PIC SM team
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Material Receiving/ Outgoing Documentation | Preservation procedure to be established and implemented during execution
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | Routing plan for heavy haulage to be part of contract
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Construction Execution | To confirm with PIC on transportation regulation
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | To confirm during detail design and vendor award
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | Nearby batching plant to be identified during site visit
TITANIUM OSBL PROJECT (FEL3) | Greenfield | Onshore - Petrochemical | Others | Transportation & Logistics | PMT to confirm on PALON services availability for future expansion in PIC.